## Slide 1: Spine Relabel Project or how to tackle a big project and stay (mostly) sane
Bree Schmidt
West Fargo Public Library

## Slide 2: Project Overview
Relabel all the collections using Cutters and replace with author’s last name (plus add genre stickers and series names/number in series)
This includes:
Adult Fiction
Adult Graphic
Large Print
Teen Fiction
Teen Graphic

## Slide 3: Let’s look at Numbers
Total of 23,740 items to relabel (give or take)
Chart: 
| Fiction | Teen Fiction | Large Print Fiction | Teen Graphic Fiction | Graphic Fiction
Column1 | 15678 | 4011 | 2665 | 901 | 485
Column2
Column3

## Slide 4: Timeline
Began the first week of June (also first week of Summer Boost, yay!)
Finished Adult Fiction on August 22
Completed replacing all Cutters on November 29
Grand total of 6 months to finish

## Slide 5: Procedure
Staff filled out a survey about what they’d like spine labels to look like
Ran numbers to figure out how many supplies to order
  Labels, label protectors (2 sizes), genre stickers, WFPL address labels
Document the rules
  Created a folder in Sharepoint
    Label template
    Missing series books Excel file
    Genre of popular authors/series
  Work on 1 shelf at a time per staff member
  Take the entire shelf to relabel so we didn’t get our spacing mixed up
  Kept track by placing a label with our name in the shelf we were currently working on
  Chart in the circ office of how far we were so they could set aside items need relabeling
  Did not change item status as the items were off the floor for such a short period of time

## Slide 6: Where we started
Prefix
Cutter
Suffix
No genre stickers

## Slide 7: Finished Product
Prefix
Author last name
Series title & number (if applicable)
Genre sticker (if applicable)

## Slide 8: Setbacks
Faded labels (UGH)
Lessons learned
  Don’t rush things – double check series names, genres
  Communicate with circulation folks

## Slide 9: Future Projects
Consolidated DVD TV series (package discs from season together)
Relabeled Junior Fiction Graphic Novels (author and series)
Decided to relabel ALL DVDs (they were/are a MESS)
Slowly working on getting all spine labels to be consistent since there have been several changes of the years
  Junior Fiction
  Easy Readers
  Picture books

## Slide 10: Questions?
Contact me
  Bree Schmidt, West Fargo Public Library
  Brianne.Schmidt@westfargond.gov
  701-515-5206 (but seriously, use email)